**The Executive Yuan Open Government National Action Plan Taskforce**

**7th Meeting - Minutes**

1. Meeting time: 2:00 pm, Monday, August 29, 2022
2. Venue: Meeting Room 610, National Development Council (NDC)
3. Chairpersons: Minister Without Portfolio and convenor Audrey Tang, National Development Council Minister and joint convenor Kung Ming-hsin, WeatherRisk Explore Inc. President and joint convenor Peng Chih-ming
4. Attendees: As shown in the attendance sheet
5. Chairperson’s Remark: (omitted)

Minute taker: Yang Yi-jun

1. Comments by members and agencies: For the verbatim transcript, see the following website:

<https://sayit.pdis.nat.gov.tw/2022-08-15-%E8%A1%8C%E6%94%BF%E9%99%A2%E9%96%8B%E6%94%BE%E6%94%BF%E5%BA%9C%E5%9C%8B%E5%AE%B6%E8%A1%8C%E5%8B%95%E6%96%B9%E6%A1%88%E6%8E%A8%E5%8B%95%E5%B0%8F%E7%B5%84%E7%AC%AC-7-%E6%AC%A1%E6%9C%83%E8%AD%B0>

1. Follow-up report on the conclusions of previous meetings (Report unit: National Development Council):

Conclusion:

Of the 5 conclusions drawn from previous meetings, it is agreed that No. 5 will be unlisted from monitoring. The rest of the conclusion will continue to be monitored.

1. Progress of the "Taiwan Open Government National Action Plan" (Report unit: National Development Council)

Conclusion:

1. Please translate the "Independent Reporting Mechanism" report of Taiwan Open Government National Action Plan into Chinese and request the administrative authorities of individual commitments to assist in informing relevant non-government organizations and enhance the connections of the Open Government National Action Plan.
2. The term of office of the first Executive Yuan Open Government National Action Plan Taskforce members will soon come to an end. After the members of the next Taskforce take office, please discuss the mechanisms for the exchange of ideas and interactions between members of the first and second-term Taskforce.
3. In addition to quantitative indicators, future progress reports for the commitments must include qualitative descriptions to illustrate the differences after the commitments are included in the Open Government National Action Plan.
4. End of meeting. (3:00 pm)