**The Executive Yuan Open Government National Action Plan Taskforce**

**5th Meeting - Minutes**

* Meeting time: 2:30 pm, Wednesday, December 22, 2021
* Venue: Executive Yuan Reception Room
* Chairpersons: Minister Without Portfolio and convenor Audrey Tang, National Development Council Minister and joint convenor Kung Ming-hsin, WeatherRisk Explore Inc. President and joint convenor Peng Chih-ming

Minute taker: Yang Yi-jun

* Attendees: As the sign-in sheet indicates
* Chairperson’s Remark: (omitted)
* Comments by members and agencies: For the verbatim transcript, see the following website: <https://pdis.tw/3FjYYXa>
* Progress on handling the conclusions of previous meetings (report unit: National Development Council):

Conclusion:

1. Of the 9 conclusions drawn from previous meetings, it is agreed that No.1, No. 4-1, No. 6, No. 7, and No. 9 will be unlisted from monitoring. The rest of the conclusions will continue to be monitored.
2. Regarding No. 3, “Depending on the characteristics and format of the data, Important Gender Statistic Database can be connected to the Government Open Data Platform of the NDC”, please compile how the data and indicators of the “Important Gender Statistics Database” are added to the “Government Open Data Platform” for non-governmental members to reference.
* Reported matters
1. Progress of the “Strengthening Digital Privacy and Personal Data Protection” commitment (report unit: National Development Council)

Conclusion: Acknowledged.

1. Progress of the “Information Disclosure Relating to the Environment” commitment (report unit: Environmental Protection Agency, Executive Yuan)

Conclusion: Acknowledged.

1. Progress of the “National Referendum Electronic Joint Signatures” commitment (report unit: Central Election Commission)

Conclusion:

1. After the launch of the electronic joint signing system for national referendums, please gather public feedback on the system during the trial period.
2. Regarding the milestone “launch of the electronic joint signing system for national referendums”, additional cyber security measures were added to cooperate with the formulation and amendment of the sub-laws to the Cyber Security Management Act, therefore the first period was not completed by December 2021. This meeting minute shall serve as the supplementary information about the milestone.
3. Progress of the “Including the Concept of Open Government into the Civic Curriculum and Teaching, and Empower Teachers” commitment (report unit: Ministry of Education)

Conclusion:

1. When designing teacher empowerment training courses and developing related teaching materials, please refer to The Indigenous Peoples Basic Law and consider how to include indigenous peoples.
2. Open government does not equal open data. It is recommended to first select a few schools, have non-governmental members explain the meaning of open government, then promote the concept with these demonstration cases.
3. Regarding the milestone “Public and private sectors work together to review the existing curricula in high schools and elementary schools and compile analysis reports”, it is necessary to continue taking inventory of the changes to technical high schools, junior high schools, and elementary schools, so first period was unable to be completed by December 2021. This meeting minute shall serve as supplementary information about the milestone.
4. Progress of the “Beneficial Ownership Transparency” commitment (report unit: Ministry of Justice)

Conclusion: Acknowledged.

1. Progress of the “Policies on Financial Transparency of Religious Groups to Close AML Loopholes” commitment (report unit: Ministry of the Interior)

Conclusion: Acknowledged.

* End of meeting. (4:10 pm)