**The Executive Yuan Open Government National Action Plan Taskforce**

**6th Meeting - Minutes**

1. Meeting time: 10:00 am, Friday, April 29, 2022
2. Venue: Video conference
3. Chairpersons: Minister Without Portfolio and convenor Audrey Tang, National Development Council Minister and joint convenor Kung Ming-hsin, WeatherRisk Explore Inc. President and joint convenor Peng Chih-ming
4. Attendees: As shown in the attendance sheet
5. Chairperson’s Remark: (omitted)

Minute taker: Yang Yi-jun

1. Comments by members and agencies: For the verbatim transcript, see the following website:  
   <https://ey.pdis.nat.gov.tw/shared/x28L5rUAGaR4ukbaEstEUxJuBamIanW3tvpe0EdvgLm>
2. Follow-up report on the conclusions of previous meetings (Report unit: National Development Council):

Conclusion:

1. Of the 7 conclusions drawn from previous meetings, it is agreed that No. 2, No. 4, and No. 7 will be unlisted from monitoring. The rest of the conclusions will continue to be monitored.
2. Regarding No. 5, "Increasing Indigenous Peoples’ Cross-domain Participation and International Linkage", the Council of Indigenous Peoples is requested to publish related information in community collaboration on the Austronesian Forum website and provide the URL to the taskforce members.
3. Regarding No. 7, "Including the Concept of Open Government into the Civic Curriculum and Teaching, and Empower Teachers", the Ministry of Education is requested to email the information on completed inventories of training courses and teaching materials to the taskforce members as reference.
4. Reported matters
5. Progress of the Independent Reporting Mechanism of Taiwan's Open Government National Action Plan (Report unit: National Development Council)

Conclusion: Acknowledged.

1. Progress of the "Youth Policy Participation" commitment (Report unit: Ministry of Education)

Conclusion:

1. With regard to the Let's Talk performance assessment, quantified indicators such as the number of sessions and participants can be used in the future as supplementary information on the resources provided by different government agencies.
2. Other contents acknowledged.
3. Progress of the "Establishing a Regional Revitalization Interactive Platform" commitment (Report unit: National Development Council)

Conclusion: Acknowledged.

1. Progress of the "Promoting Gender-inclusive Dialogue and Participation" commitment (Report unit: Department Gender Equality, Executive Yuan)

Conclusion: Acknowledged.

1. Progress of the "Promoting New Immigrant Public Participation and Development" commitment (Report unit: Ministry of the Interior)

Conclusion: Acknowledged.

1. Progress of the "Promoting Public Participation on Hakka Issues" commitment (Report unit: Hakka Affairs Council)

Conclusion: Acknowledged.

1. Progress of the "Establishing and Improving the Government Procurement Integrity Platform" commitment (Ministry of Justice, 10 minutes)

Conclusion: Acknowledged.

1. Special Motions

New commitments for Open NetZero, Open Climate platform: The net zero pathway proposed for Taiwan to combat climate change requires communication with the public. The current dialogue consists mainly of communication between specialists and government officials and not yet been expanded to other sectors. The open government platform should be used to create Open NetZero, Open Climate platform to provide the public with communication channels so that they can learn more about climate change and build a national consensus for combating climate change. (Proposer: Joint convener Peng Chih-ming and committee members Lin Tzu-lun, Wu Min-hsuan, and Geng Lu)

Conclusion: The National Development Council and the Environmental Protection Administration, Executive Yuan are requested to assemble related agencies and members of the taskforce for discussions.

1. End of meeting. (12:00 pm)